## Sheet1
Sprint Capacity Planner
| Max Limit | Team Hours |  |  | Sprint Days
Team Members | 5 |  | Team Member | Allocation | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Sprint Length (Days) | 7 |  | Adrian Visla | 100% | 0 | 2 | 4 | 3 | 1 | 3 | 1
Hours per day | 4 |  | Paul Martinas | 100% | 3 | 2 | 2.5 | 1.5 | 1.5 | 2 | 0
Focus Factor | 65% |  | Andrei Roman | 100% | 3 | 3 | 4 | 3 | 1 | 0 | 1
Daily stand-ups (Hours/Sprint) | 0.25 | 8.75 | Robert Roman | 100% | 4 | 3 | 3 | 2.5 | 3 | 1 | 0
Sprint Planning Duration (Hours/Sprint) | 1 | 5 | Stefan Boboc | 100% | 1 | 3 | 4 | 0.5 | 0.5 | 4 | 4
Sprint Review (Hours/Sprint) | 0.4 | 2
Sprint Retrospective (Hours/Sprint) | 1 | 5
Sprint Refinements (Hours/Sprint) | 0.75 | 3.75
Other meetings (Hours/Sprint) | 1 | 5
Total Capacity (Hours) | 75
Total Meeting Time (Hours) | 29.5 |  | Total Team Time (Hours) |  | Sprint Days 10: 75
Focus Time (Hours) | 15.925
Plan Capacity (Hours) | 29.575
Plan Capacity (Days) | 3.6969
Note on D19: the sum of sprint tasks estimation should not exceed this number -Oana Adriana Soica